## Communication Plan
Communication Plan: (Project Name)
The following is a list of communication activities to consider. Please do not limit your list to these examples.
ID # | Communication Name | Target Audience | Purpose | When / Frequency | Type / Method | Responsible | Date Completed | Template Name and Location* (If applicable)
Sample 1 | Discovery Meeting | All stakeholders | To identify all stakeholders and provide a forum for all project team members to discuss schedule, scope, team, and other issues. | At the start of the Project Initiation phase. | Meeting
Sample 2 | Project Kick-off Meeting | All stakeholders | To familiarize the project team with the project, review the project charter, roles, expectations, high level timeline and receive buy-in from all project participants, Future meeting schedules will be defined and discussed and meeting minutes will be documented. | At the end of the Project Initiation phase. | Meeting
Sample 3 | Communication to end users | Users of the application | Inform users of the changes to the existing application | Two weeks before implementation; Two days before implementation | Targeted email communication to end users
Sample 4 | General information to campus about upcoming changes | Campus | Communicate general information to campus about coming changes | Two months before implementation about changes; Two weeks update about changes; Two days before implementation | Mass mail to campus
Sample 5 | Use case examples | Users of the application | Communicate the changes in processes or functionality demonstrated through Use Cases
Sample 6 | FAQ | Users of the application; Campus | Document and communicate Frequently Asked Questions about the application changes | Two months before implementation; Updated bi-weekly as new questions are received | Web Page
Sample 7 | Press Release | Campus and external community | Communicate general information to campus about coming changes | Two months before implementation | Newspaper, Today@Wayne, website
Sample 8 | Project Reconnect Meeting | Entire project team | To review detailed plans: Tasks, Assignments, Action items, Change Requests | Regularly Scheduled. Weekly is recommended for entire team. Weekly or twice-weekly for sub-teams as appropriate. | Meeting with standardized agenda and minutes.
Sample 9 | Sub team working meetings or discussions | Individual meetings for sub-teams, technical team, and Functional teams as appropriate. | To discuss specific topics, resolve issues as a group, or work on shared tasks. | As needed | Meeting with standardized agenda and minutes.
Sample 10 | Sponsor Meetings | Sponsor(s) and Project Manager | Update Sponsor(s) on status and discuss critical issues. Seek approval for changes to Project Plan. | Regularly scheduled. Recommended biweekly or monthly and also as needed when issues cannot be resolved or changes need to be made to Project Plan | Meeting
Sample 11 | Steering Committee / Executive Oversight Meetings (This applies to larger projects) | Executive Sponsor(s) and Project Manager | Update Sponsor(s) on status and discuss critical issues. Seek approval for changes to Project Plan. | Regularly scheduled. Recommended monthly or quarterly. As needed when issues cannot be resolved or changes need to be made to Project Plan. | Meeting with standard reporting package.
Sample 12 | Project Closure Meeting | Project Manager, Project team, key stakeholders, and sponsor(s) | Conducting the post project review meeting will allow the project team and the customer project participants and leadership to gather one last time to ensure that there are no outstanding issues or work. This will also provide a forum to review lessons learned throughout the project. | End of project or end of major phase | Meeting with standardized agenda and minutes.
Sample 13 | Periodic Demos and Target Presentations | Specific Focus Groups or End Users. | To gain input from specific groups and keep them informed of the Project’s status. | As needed to demonstrate functionality and receive feedback in a timely manner | Presentation and Discussion
Sample 14 | Other | TBD by the team | General communications | As needed
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Note on B4: What Needs to be Communicated?
Note on C4: Who Needs this Information?
Note on E4: How Often will it be Communicated? (E.g. As needed, once, weekly, etc.)
Note on F4: How will it be Communicated? (E.g. Name of Report, MS Teams, meeting, mass email, Academica, etc.)
Note on G4: Who is Responsible for Communicating this Information?
Note on I4: *If the communication item is a document, this field refers to where the document template is stored. If templates do not currently exists, the team must create the template as part of the project scope.